## Budge Estimate Worksheet
Client: | MEATS by ANDY
Date: | 2023-03-05
ESTIMATED BUDGET
# | Requirements | Hours | Cost | # | Equipment and Testing | Hours | Cost
1. | Assemble Project Team with HR and the department heads | 64 | 3520 | 20. | Evaluate platform requirements | 72 | 3960
2. | Develop project estimate (preparation of contract/estimate, digital and paper file management, tracking hours, invoicing) | 63 | 3465 | 21. | Design support system specifications | 56 | 3080
3. | Meetings, phone calls, email correspondence to validate the requirements and approach with departments | 88 | 4840 | 22. | Place orders for procurement of needed equipment | 16 | 880
4. | Publish final project specifications and receive sign off/approval and organize the Project Schedule in MS Project | 72 | 3960 | 23. | Receive and install equipment purchases | 64 | 3520
| Total |  | 15785 | 24. | Test API and fix any bugs that may appear. | 88 | 4840
# | Design | Hours | Cost | 25. | Testing, troubleshooting and finalizing installed equipment | 72 | 3960
5. | Develop the design specifications for the project | 264 | 14520 |  | Total |  | 20240
6. | Evaluate the design impact on exisiting systems and processes | 48 | 2640 | # | Completion and Wrap-Up | Hours | Cost
7. | Develop the design of desktop and smartphone applications. | 128 | 7040 | 26. | Complete final steps of documentation and training | 64 | 3520
8. | Design sales performance report and site visit reports | 48 | 2640 | 27. | Prepare written communication of project completion | 24 | 1320
9. | Forward design specifications to the training and documentation staff | 24 | 1320 | 28. | Uploading, testing and finalizing completed project | 96 | 5280
10. | Publish the design and obtain the sign off/approval for users | 19.2 | 1056 | 29. | Client training | 72 | 3960
| Total |  | 29216 | 30. | Obtain sign off/approval for system implementation | 30.4 | 1672
# | Development | Hours | Cost | 31. | System Launch | 24 | 1320
11. | Organize and manage the development teams for the project | 80 | 4400 |  | Total |  | 17072
12. | Organize the team meetings to provide an overview to the development teams | 32 | 1760 | # | Final Calculations & Totals
13. | Distribute and review the design documantation with the teams | 24 | 1320 | 32. | ACTUAL ESTIMATED HOURS/COSTS | 1858.2 | 102201
14. | Enhance website functionalities | 89.6 | 4928 | 33. | + 10-20% CONTINGENCY ALLOWANCE | 185.82 | 10220.1
15. | Provide updates to the Testing/Quality Assurance teams | 32 | 1760 | 34. | ESTIMATED HOURS/COSTS SUBTOTAL | 2044.02 | 112421.1
16. | Complete the first phase of testing | 48 | 2640 | 35. |  |  |  | 55
17. | Review the initial test results and provide feedback for updates | 56 | 3080 | 36. | Project EXPENSES |  | 14150
18. | Complete the second and final phase of testing | 80 | 4400 | 37. | TOTAL PROJECT ESTIMATE ($) |  | 126571.1
19. | Distribute the final development to the training and documentation teams | 24 | 1320
| Total | 465.6 | 25608
Exp. | Detail | Cost |  |  | Cost Basis | Cost
1 | Software | 4000 |  |  | System Analyst | 55
2 | Office equipment | 1000 |  |  | System Programmer | 47
3 | Fees, Dues, and subcriptions | 500 |  |  | Tester | 43
4 | Rent, Utilities, and tech supplies | 4800
5 | Meals & Entertainment | 500
6 | Mileage and Hotel | 2200
7 | Legal fees | 1000
9 | Printing and copying expense | 150
| Total: | 14150
Note on J26: Insert Hourly Rate Here